## Excel Gantt Chart Template
Gantt Chart |  |  |  |  | DATE
Diego's Thesis |  |  | DURATION (days)
START DATE | END DATE | DESCRIPTION
2018-01-20 | 2018-02-05 | INTRODUCTION | 15 |  |  | Collection DATA
[6 empty] | Writing | Collection DATA
2018-02-05 | 2018-02-28 | BACKGROUND | 23 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-02-05 | 2018-02-15 | -State of Art in Actuation | 10 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-02-15 | 2018-02-24 | -Microstructure of Drawn Polymer Monofilament | 9 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-02-24 | 2018-02-28 | -Material modeling | 4 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-02-28 | 2018-05-15 | CHARACTERIZATION OF THE PRECURSOR MATERIAL | 75 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-02-28 | 2018-03-02 | -Manufacturing, processing and test methods | 2 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-03-02 | 2018-03-18 | -Axial Modulus as a Function of temperature | 16 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-03-18 | 2018-03-28 | -Radial Modulus as a Function of Temperature | 10 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-03-28 | 2018-04-14 | -Shear Modulus as a Function of Temperature | 16 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-04-14 | 2018-04-20 | -Poisson Ratio | 6 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-04-20 | 2018-05-02 | -Axial Thermal Contraction | 12 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-05-02 | 2018-05-15 | -Radial Thermal Expansion | 13 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-05-15 | 2018-06-30 | PREDICTION WITH THE FOUND MATERIAL PROPERTIES | 45 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-05-15 | 2018-06-07 | -Precursor Fiber under Load and Temperature | 22 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-06-07 | 2018-06-30 | -Twisted Fibers under Temperature Changes under no Load. Experiments vs. Model | 23 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-06-30 | 2018-07-05 | CONCLUSION | 5 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-07-05 | 2018-07-20 | THESIS CORECTIONS | 15 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-07-20 | 2018-07-30 | PRESENTATION | 10 |  |  | Collection DATA | Writing
[6 empty] | Writing | Collection DATA
2018-07-31 | 2018-08-01 | DEFENSE | 1 |  |  |  | Writing
2018-08-01 | 2018-08-12 | FINAL THESIS CORRECTIONS | 11 |  |  | Collection DATA
[6 empty] | Writing | Collection DATA
Writing
www.officetimeline.com
2018-01-20 | 2018-02-05 | 15
2018-01-20 | 2018-02-05 | 15
2018-02-05 | 2018-02-28 | 23
2018-02-05 | 2018-02-28 | 23
2018-02-05 | 2018-02-15 | 10
2018-02-05 | 2018-02-15 | 10
2018-02-15 | 2018-02-24 | 9
2018-02-15 | 2018-02-24 | 9
2018-02-24 | 2018-02-28 | 4
2018-02-24 | 2018-02-28 | 4
2018-02-28 | 2018-05-15 | 75
2018-02-28 | 2018-05-15 | 75
2018-02-28 | 2018-03-02 | 2
2018-02-28 | 2018-03-02 | 2
2018-03-02 | 2018-03-18 | 16
2018-03-02 | 2018-03-18 | 16
2018-03-18 | 2018-03-28 | 10
2018-03-18 | 2018-03-28 | 10
2018-03-28 | 2018-04-14 | 16
2018-03-28 | 2018-04-14 | 16
2018-04-14 | 2018-04-20 | 6
2018-04-14 | 2018-04-20 | 6
2018-04-20 | 2018-05-02 | 12
2018-04-20 | 2018-05-02 | 12
2018-05-02 | 2018-05-15 | 13
2018-05-02 | 2018-05-15 | 13
2018-05-15 | 2018-06-30 | 45
2018-05-15 | 2018-06-30 | 45
2018-05-15 | 2018-06-07 | 22
2018-05-15 | 2018-06-07 | 22
2018-06-07 | 2018-06-30 | 23
2018-06-07 | 2018-06-30 | 23
2018-06-30 | 2018-07-05 | 5
2018-06-30 | 2018-07-05 | 5
2018-07-05 | 2018-07-20 | 15
2018-07-05 | 2018-07-20 | 15
2018-07-20 | 2018-07-30 | 10
2018-07-20 | 2018-07-30 | 10
2018-07-31 | 2018-08-01 | 1
2018-07-31 | 2018-08-01 | 1
2018-08-01 | 2018-08-12 | 11
2018-08-01 | 2018-08-12 | 11
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download Office Timeline Plus Edition for PowerPoint.
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of PowerPoint. Copy your Excel table paste it into Office Timeline Plus or import it.
3. Click the green check mark to instantly produce you timeline slide.
Collecting Data
Writing
Completed Work

## Excel Timeline Template
Excel Timeline Template
Enter Your Project Details Here
DATE | DESCRIPTION | POSITION
2016-05-10 | Kick Off | 1
2016-06-07 | Milestone 1 | 2
2016-07-21 | Milestone 2 | 1
2016-08-01 | Checkpoint A | 4
2016-09-20 | Milestone 3 | 3
2016-10-30 | Milestone 4 | 2
2016-12-20 | Checkpoint B | 3
2017-01-30 | Milestone 5 | 4
2017-02-10 | Milestone 6 | 1
2017-03-30 | Milestone 7 | 2 |  | `
2017-05-20 | Checkpoint C | 3
2017-05-30 | Sign Off | 1
Make beautiful timelines in PowerPoint for important meetings. |  |  | Download #1 Free timeline add-in for PowerPoint
www.officetimeline.com
https://www.officetimeline.com/download
Note on D6: Project Timeline Tip: The position values vary the height of your Milestones and are used to prevent text overlap. Using negative numbers will place Milestones labels below the timeband. If you position a Milestone below the timeband click on its label in the chart to set its Label Position to below.
Note on B17: Project Timeline Tip: To add more Milestones insert new rows into this table and then use the Select Data field to update your Series as show in step # 3 here: https://www.officetimeline.com/excel-timeline
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download Office Timeline Plus Edition for PowerPoint.
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of PowerPoint. Copy your Excel table paste it into Office Timeline Plus or import it.
3. Click the green check mark to instantly produce you timeline slide.