## Sheet1
GANTT DIAGRAM for TPA project
PROJECT'S APPROACHES | Start Date | Time interval | End Date
Literature Review | 2016-11-01 | 50 | 2016-12-21
Proposal Project | 2016-11-11 | 60 | 2017-01-10 | 42675
Manufacture First Specimen | 2017-01-10 | 10 | 2017-01-20
Test First Specimen | 2017-01-11 | 25 | 2017-02-05 | 43388
Develop Theoretical model | 2017-01-11 | 80 | 2017-04-01
Manufacture a Set of Specimens | 2017-02-15 | 15 | 2017-03-02
Test the Set of Specimens | 2017-03-01 | 60 | 2017-04-30
Match theoretical and Experimental Results | 2017-04-25 | 15 | 2017-05-10
Develop a Simulation | 2017-04-26 | 80 | 2017-07-15
Match theoretical, Experimental and Simulation Results | 2017-07-27 | 10 | 2017-08-06
Heat transfer actuation on the TPA as an Input. | 2017-07-28 | 30 | 2017-08-27
Build an Application for a morphing Air Machine. | 2017-08-30 | 90 | 2017-11-28
Test this Morphing Machine | 2017-11-30 | 120 | 2018-03-30
Make Improvements | 2018-03-31 | 100 | 2018-07-09
Defence Thesis
| 2016-11-01 | 2018-10-15 | -713
Formulas:
End Date = [Start Date]+[Time interval]